## Slide 1: EDDI summary of the year 2016
M. Gorley, CCFE
WPMAT
1-T003-D001 (Deliverable-ID)

## Slide 2: Deliverable Specification
Deliverable: Summary report on EDDI Co-ordination for year 2016
Objectives in 2016:
  Organise, lead and record progress and review meetings to assure delivery against the WPMAT Project Management Plan
  Interact with PMU and Project Leader as necessary in order to assure:
    delivery against WPMAT Project Management Plan;
    successful engagement of relevant partners beyond EUROFUSION
  Facilitate structured discussions with all projects and work packages that need to exchange materials information.
  Maintain and update implement the EDDI interface project management plan
  Delivery, maintenance and evolution of project infrastructure - to include IDM structure, technical specifications, progress reports and project management plans
  Provide annual executive summary of WPMAT EDDI activities for circulation amongst WPMAT Project Board, Project Leader & PPPT Programme Unit
Effort: 0.5 ppy

## Slide 3: EDDI Key goals
WBS 1.1 – Update MTRL, enhance WPMAT and EDDI visibility & reputation
WBS 1.2 – Release of MPH V1 and V2, pilot FM MPH
WBS 1.3 – Initial rollout of tools/methodologies to designers, 1st draft release of DDC
WBS 1.4 – Round Robin testing (completion) and first results from initial “real” testing

## Slide 4: General concerns
WBS 1.1:
EDDI under scrutiny and need to be more visibly integrated within wider DEMO plans
Closer interactions with WPBB a key requirement in 2017
WBS 1.2:
How to make full MPH for all DEMO materials (W, FMs, novel materials).
Lack of collaboration with F4E on MPH and database (no EU MPH).
How to make the materials database international, and long lasting (GenIV collaborations?)
WBS 1.3:
Need to a agree a realistic strategy for Design Criteria across DEMO to be agreed at all levels (Top, deign teams and EDDI).
International and industrial support required but limited to date (e.g. AREVA issues)
Determine engagement options with Codes and Standards organisations
WBS 1.4:
Slow responses with Round Robin (was this a useful exercise or not?).
Reactive nature of test requests and future need for significant testing requirements.

## Slide 5: Key achievements of the year
WBS 1.1 – Enhanced visibility of EDDI with EUROfusion, good interactions with: WPD&C, DIV, S&E and PMI
WBS 1.2 – Release of MPH V1, ready for release of MPH V2 (and FM MPH?)
Good interactions with WPMAT gathering data on R&D materials, better use of templates for data storage.
WBS 1.3 – Well attended EDDI-designers meeting in March. Release of CFA-tool. Better understanding of EU roadmap for Fusion design criteria based on F4E meetings.
WBS 1.4 – Initial test request results obtained (providing data for update of creep fatigue interaction diagram).

## Slide 6: Deliverable Results
Objectives in 2016:
  Organise, lead and record progress and review meetings to assure delivery against the WPMAT Project Management Plan
  Interact with PMU and Project Leader as necessary in order to assure:
    delivery against WPMAT Project Management Plan;
    successful engagement of relevant partners beyond EUROFUSION
  Facilitate structured discussions with all projects and work packages that need to exchange materials information.
  Maintain and update implement the EDDI interface project management plan
  Delivery, maintenance and evolution of project infrastructure - to include IDM structure, technical specifications, progress reports and project management plans
  Provide annual executive summary of WPMAT EDDI activities for circulation amongst WPMAT Project Board, Project Leader & PPPT Programme Unit

## Slide 7
Work plan for 2017, initial review

## Slide 8: Reminder: EDDI - Grant deliverables
WP | ID | Title | Due date | Update date
MAT | D25.14 | MAT.D06.1 MPH: (1st formal release) | Dec-14 | Mar-16
MAT | D25.15 | MAT.D06.2 MPH: (2nd formal release) | Dec-15 | Jun-17
MAT | D25.16 | MAT.D06.3 MPH: (3rd formal release) | Dec-18 | 
MAT | D25.18 | MAT.D07.1b Design criteria, codes and standards rules Intermediate report | Dec-16 | 
MAT | D25.20 | MAT.D07.2b Design criteria, codes and standards rules : Final report | Dec-18 | 

## Slide 9: Initial ideas on 2017 high level aims
Establish and gain approval for draft EU roadmap for Design Criteria in fusion
Develop “draft” MPH chapter for “baseline” Tungsten & extend FM MPH
Continue to grow WPMAT group interactions with greater establishment of MTRL and materials Database
Better interaction with DEMO design via SEOP role and increased collaboration with DIV and BB
Conclude and summarise multiple test request to support rule development/validation.
Increase international and industrial collaborations as much as possible
Start establishing collaborative projects with IREMEV group

## Slide 10: 2017 Task Specification Proposals Review (1.1)
WBS 1.1:
Sub project lead, 0.5ppy (CCFE)
MTRL update and establish wider release, 0.3ppy (CCFE)
WPMAT SEPOC role (learn DOORS and act as liaison), 0.2ppy (CCFE)
Optional, extent DEMO surveillance scheme review, 0.5ppy (NRG)

## Slide 11: 2017 Task Specification Proposals Review (1.2)
WBS 1.2:
Materials database FM, 0.2ppy (MTA)
Materials database HHFM, AS, 0.3ppy (KIT)
Materials database support CuCrZr, 0.1ppy (CCFE)
Extend and further develop FM – MPH, 0.4ppy (MTA)
Lead development of “draft” MPH on “baseline” W, 0.4ppy (KIT)
Support development of “draft” MPH on “baseline” W, 0.5ppy (CCFE)
From 2016: WPDIV materials data, 0.2ppy (CCFE)

## Slide 12: 2017 Task Specification Proposals Review (1.3)
WBS 1.3:
Continue Brittle fracture work, 0.3ppy (KIT)
Conclude Creep-fatigue interaction & evaluate high temperature modifying effects relevant for DDC, 0.2ppy (KIT)
Continue (and finalise) CFA-tool, 0.5ppy, (KIT)
Supporting role on Grain Modelling Fatigue, 0.1ppy? (CEA)
Review plastic flow localisation rule for DDC, 0.4ppy, (CCFE)
Review fatigue rules, effect of joints, 0.4ppy, (CCFE)
Review fatigue rules, effect of crack propagation, 0.4ppy (CCFE)
Review fatigue rules, effects of Residual stress and new ANSYSIS analysis, 0.4ppy (CCFE)
Review exhaustion of ductility for DDC, 0.5ppy (CCFE)
Extend review of partial factors use and overview review of DDC by industry, 0.5 (ind) ppy, (CCFE/AMEC)
From 2016: Finish review of DDC, 0.5 (ind) ppy (CCFE/AMEC)

## Slide 13: 2017 Task Specification Proposals Review (1.4)
WBS 1.3:
  Lead EDDI testing campaigns (RR and test requests), 0.6ppy (ENEA)
  Support EDDI testing campaigns (RR and test requests), 0.3ppy (KIT)

## Slide 14: EDDI monitoring meeting conclusions
Which goals/deliverables have been reached?
  26 deliverables set to be achieved, 2 delayed
Which goals/deliverables have not been reached? Why? Actions required or planned?
  AMEC deliverable, delayed, no modifications recommended
  WPDIV materials data task, delayed, updates to be implemented
Comments on the Workplan 2017 and PMP: Is the WP still feasible? Is adjustment required due to your results? What is your outlook?
  Grant deliverables are achievable although expectations must be set.
  Proposed 2017 work plan to realise key goals for EDDI
  Greater visibility of work and DEMO wide agreement of strategy must be a key target for 2017

## Slide 15: Many thanks to everyone for your attendance and efforts this year
WPMAT

## Slide 16
Objective(s):
Review your 5 years objectives (i.e. your offer in answer to the call for participation in 2013/14)
Midterm–Review: Objectives-Status for the 5 year period
EDDI is essentially tasked with a range of strategically vital, long term and challenging tasks within the design of DEMO including:
Developing and implementing all materials interactions (information supply) for DEMO
Developing and running a materials management framework to enable assessments and appraisals of all materials proposed for DEMO
Developing, obtaining data for and maintaining a vast material database to support the development of a materials property handbook, eventually to include data from un-precedence conditions to match DEMO requirements
Developing and completing a DEMO specific materials property handbook to contain all the required materials data (accurately and statistically scrutinised with full data provenance) required to design DEMO
Developing a new set of design criteria to enable the design of DEMO plasma facing components (blanket and Divertor) based on the unprecedented environmental conditions to be faced, going beyond any existing framework
The 5 year objectives was essentially to establish the group and lay strong foundations for the completion of these long term tasks.

## Slide 17
Midterm–Review: Objectives-Status for the 5 year period
Achievement and status:
Report the achievements
Report as well on failures (long-term as important as appearing all time “brilliant”)
How far are you wrt to schedule (ahead/behind)
Impact on the project
Interaction with other tasks/work-packages ….
Outlook:
Next steps ahead
How do you rate them (eg. challenge/risk)
… other elements you consider important ….

## Slide 18
Logos of the official WPMAT participants. Note: Some universities and labs are grouped in certain countries and, therefore, appear officially as only one RU (CIEMATand 2 sections of ENEA). Nevertheless, you are invited to add your own logo!