## Slide 1: EDDI summary of the year 2016
M. Gorley, CCFE
WPMAT
1-T003-D001

## Slide 2: Deliverable Specification
Deliverable: Summary report on EDDI Co-ordination for year 2016
Objectives in 2016:
  Organise, lead and record progress and review meetings to assure delivery against the WPMAT Project Management Plan
  Interact with PMU and Project Leader as necessary in order to assure:
    delivery against WPMAT Project Management Plan;
    successful engagement of relevant partners beyond EUROFUSION
  Facilitate structured discussions with all projects and work packages that need to exchange materials information.
  Maintain and update implement the EDDI interface project management plan
  Delivery, maintenance and evolution of project infrastructure - to include IDM structure, technical specifications, progress reports and project management plans
  Provide annual executive summary of WPMAT EDDI activities for circulation amongst WPMAT Project Board, Project Leader & PPPT Programme Unit
Effort: 0.5 ppy

## Slide 3: EDDI big ticket items
WBS 1.1 – Update MTRL, enhance WPMAT and EDDI visibility & reputation
WBS 1.2 – Release of MPH V1 and V2, pilot FM MPH
WBS 1.3 – Initial rollout of tools/methodologies to designers, 1st draft release of DDC
WBS 1.4 – Round Robin testing (completion) and first results from initial “real” testing

## Slide 4: General concerns
WBS 1.1:
EDDI under scrutiny and need to be more visibly integrated within wider DEMO plans
Closer interactions with WPBB a key requirement in 2017
WBS 1.2:
How to make full MPH for all DEMO materials (W, FMs, novel materials).
Lack of collaboration with F4E on MPH and database (no EU MPH).
WBS 1.3:
Need to a agree a realistic strategy for Design Criteria across DEMO to be agreed at all levels (Top, deign teams and EDDI).
International and industrial support required but limited to date (e.g. AREVA issues)
WBS 1.4:
Slow responses with Round Robin (was this useful or not?).
Reactive nature of test requests and future need for significant testing requirements.

## Slide 5: Key achievements of the year
WBS 1.1 – Enhanced visibility of EDDI with EUROfusion, good interactions with other WPs
WBS 1.2 – Release of MPH V1, ready for release of MPH V2 (and FM MPH?)
Good interactions with WPMAT gathering data on R&D materials, better use of templates for data storage.
WBS 1.3 – Well attended EDDI-designers meeting in March. Release of CFA-tool.
Initial DDC release set for December
Better understanding of EU roadmap for Fusion design criteria based on F4E meetings.
WBS 1.4 – Initial test request results obtained (providing data for update of creep fatigue interaction diagram).
Initial RR test providing data and identified aceptable/unaceptable RUs for future testing

## Slide 6
Work plan for 2017, initial review

## Slide 7: Reminder: EDDI - Grant deliverables
WP | ID | Title | Due date | Update date
MAT | D25.14 | MAT.D06.1 MPH: (1st formal release) | Dec-14 | Mar-16
MAT | D25.15 | MAT.D06.2 MPH: (2nd formal release) | Dec-15 | Jun-17
MAT | D25.16 | MAT.D06.3 MPH: (3rd formal release) | Dec-18 | 
MAT | D25.18 | MAT.D07.1b Design criteria, codes and standards rules Intermediate report | Dec-16 | 
MAT | D25.20 | MAT.D07.2b Design criteria, codes and standards rules : Final report | Dec-18 | 

## Slide 8: Initial ideas on 2017 high level aims
Establish and gain approval for draft EU roadmap for Design Criteria in fusion
Develop “draft” MPH chapter for “baseline” Tungsten & extend FM MPH
Continue to grow WPMAT group interactions with greater establishment of MTRL and materials Database
Better interaction with DEMO design via SEOP role and increased collaboration with DIV and BB
Conclude and summarise multiple test request to support rule development/validation.
Increase international and industrial collaborations as much as possible
Start establishing collaborative projects with IREMEV group

## Slide 9: EDDI 2017 budget (as of now)
CCFE: 3.50 lab-ppy
  (+ 0.5 ppy for sPL)
KIT: 2.0 lab-ppy, 40k HW
  (HW to be converted into ppy – numbers unconfirmed)
Wigner RCP (HAS/MTA): 0.6 lab-ppy
ENEA-CNR: 0.6 lab-ppy, 20k HW
Industry (via CCFE): 0.5 Ind. ppy
FOM-NRG: 0.5 lab-ppy
  (was down to zero on 2015 & 2016 – involvement unconfirmed)
CEA: 0.1 lab-ppy

## Slide 10: 2017 Task Specification Proposals Review (1.1)
WBS 1.1:
Sub project lead, 0.5ppy (CCFE)
MTRL update and establish wider release, 0.3ppy (CCFE)
WPMAT SEPOC role (learn DOORS and act as liaison), 0.2ppy (CCFE)
Optional, extent DEMO surveillance scheme review, 0.5ppy (NRG)

## Slide 11: 2017 Task Specification Proposals Review (1.2)
WBS 1.2:
Materials database FM, 0.2ppy (MTA)
Materials database HHFM, AS, 0.3ppy (KIT)
Materials database support CuCrZr, 0.1ppy (CCFE)
Extend and further develop FM – MPH, 0.4ppy (MTA)
Lead development of “draft” MPH on “baseline” W, 0.4ppy (KIT)
Support development of “draft” MPH on “baseline” W, 0.5ppy (CCFE)
From 2016: WPDIV materials data, 0.2ppy (CCFE)

## Slide 12: 2017 Task Specification Proposals Review (1.3)
WBS 1.3:
Continue Brittle fracture work, 0.3ppy (KIT)
Conclude Creep-fatigue interaction & evaluate high temperature modifying effects relevant for DDC, 0.2ppy (KIT)
Continue (and finalise) CFA-tool, 0.5ppy, (KIT)
Supporting role on Grain Modelling Fatigue, 0.1ppy? (CEA)
Review plastic flow localisation rule for DDC, 0.4ppy, (CCFE)
Review fatigue rules, effect of joints, 0.4ppy, (CCFE)
Review fatigue rules, effect of crack propagation, 0.4ppy (CCFE)
Review fatigue rules, effects of Residual stress and new ANSYSIS analysis, 0.4ppy (CCFE)
Review exhaustion of ductility for DDC, 0.5ppy (CCFE)
Extend review of partial factors use and overview review of DDC by industry, 0.5 (ind) ppy, (CCFE/AMEC)
From 2016: Finish review of DDC, 0.5 (ind) ppy (CCFE/AMEC)

## Slide 13: 2017 Task Specification Proposals Review (1.4)
WBS 1.4:
  Lead EDDI testing campaigns (RR and test requests), 0.6ppy (ENEA)
  Support EDDI testing campaigns (RR and test requests), 0.3ppy (KIT)

## Slide 14: EDDI monitoring meeting conclusions
Which goals/deliverables have been reached?
  26 deliverables set to be achieved, 2 delayed
Which goals/deliverables have not been reached? Why? Actions required or planned?
  AMEC deliverable, delayed, no modifications recommended
  WPDIV materials data task, delayed, updates to be implemented
Comments on the Workplan 2017 and PMP: Is the WP still feasible? Is adjustment required due to your results? What is your outlook?
  Grant deliverables are achievable although expectations must be set.
  Proposed 2017 work plan to realise key goals for EDDI
  Greater visibility of work and DEMO wide agreement of strategy must be a key target for 2017

## Slide 15: Many thanks to everyone for your attendance and efforts this year
WPMAT

## Slide 16: Deliverable Results
Objectives in 2016:
  Organise, lead and record progress and review meetings to assure delivery against the WPMAT Project Management Plan
  Interact with PMU and Project Leader as necessary in order to assure:
    delivery against WPMAT Project Management Plan;
    successful engagement of relevant partners beyond EUROFUSION
  Facilitate structured discussions with all projects and work packages that need to exchange materials information.
  Maintain and update implement the EDDI interface project management plan
  Delivery, maintenance and evolution of project infrastructure - to include IDM structure, technical specifications, progress reports and project management plans
  Provide annual executive summary of WPMAT EDDI activities for circulation amongst WPMAT Project Board, Project Leader & PPPT Programme Unit

## Slide 17
Objective(s):
Review your 5 years objectives (i.e. your offer in answer to the call for participation in 2013/14)
Midterm–Review: Objectives-Status for the 5 year period
EDDI is essentially tasked with a range of strategically vital, long term and challenging tasks within the design of DEMO including:
Developing and implementing all materials interactions (information supply) for DEMO
Developing and running a materials management framework to enable assessments and appraisals of all materials proposed for DEMO
Developing, obtaining data for and maintaining a material database to enable the development of a materials property handbook, eventually to include data from un-precedence conditions to match DEMO requirements
Developing and implementation of a DEMO specific materials property handbook to contain all the required materials data (accurately and statistically scrutinised with full data provenance) required to design DEMO
Developing a new set of design criteria to enable the design of DEMO plasma facing components (Blanket and Divertor) including unprecedented environmental conditions, going beyond any existing framework
The 5 year objectives was essentially to establish the group and lay strong foundations for the completion of these long term tasks.

## Slide 18
Midterm–Review: Objectives-Status for the 5 year period
Achievement and status:
Report the achievements
EDDI group established and integrated into WPMAT and PPP&T
Many (not all) key interfaces started e.g. links with WPMAT and WPDIV
A materials management framework developed and initial materials assessment started
A database management structure and materials data collection methods invented and established for WPMAT and instigated within all materials R&D projects (e.g. advanced steels)
Structure for a DEMO specific materials property handbook established
An initial chapter on baseline steel (eurofer) for DEMO materials property handbook, including collation of vast number of materials data records (fully scrutinized and reviewed), input to provide key materials information for the design of DEMO - available now.
Based on pre-existing gap analysis a framework for the development of new design criteria specific for the needs of DEMO was established. This includes going far beyond existing codes and standards for nuclear reactors by incorporating in-elastic analysis an accommodation of complex components with multi material joints.
Engagement of industrial partners with development of DEMO design criteria
Initial tools and methodologies for new ways of design analysis for DEMO components, realised in the EDDI project has been relased to PPP&T design groups
Base on the need for significant materials testing a structured methodology, inlcudin templates and reviews, for performing database and design rule validation tests has been established.
Round robin testing within EUROfusion revealed which laboratories can be relied upon to provide test data, with some research Units results identified as below “acceptance criteria”.
Initial tests to vitiated new “creep fatigue” design criteria and key data for the DEMO materials database have been realized within EDDI testing group

## Slide 19
Midterm–Review: Objectives-Status for the 5 year period
Achievement and status:
Report the achievements
Report as well on failures (long-term as important as appearing all time “brilliant”)
Materials management framework established but developed slower than anticipated and not propagated to key stakeholders or upper management structures efficiently
Very few links with external orgnisations and industry (F4E, IO, GenIV community, AREVA, JAEA, US DoE, ..) agreed upon, often not for a lack of efforts from EDDI, limiting alignment of tasks and concepts that could accelrate progress.
Challenges in obtaining the necessary “properties/requirements” from designer, in particular for non-structural materials e.g. diagnostic windows. Caused but poor communications and hampered progress, now being addressed.
How far are you wrt to schedule (ahead/behind)
In respect of 2018 objectives (and grant deliverables) EDDI is on track
Interaction with other tasks/work-packages.
WPMAT: AS, HHFM, FM - very strong and frequent WPMAT: IREMEV - limited but set to grow WPDIV: good and frequent but needs continued growth WPBB: acceptable but needs significant more interactions in coming years WPD&C, WPH&CD: limited to date but positive interactions this year set to grow WPS&E, WPRH, WPPCF: engaged but limited interaction during pre-conceptual design phase F4E, IAEA, JAEA, and Broader approach: Basic interactions to support some alignment of concepts but needs growth

## Slide 20
Midterm–Review: Objectives-Status for the 5 year period
Outlook:
Next steps ahead
2017 (and thoughts for 2018) task specification should enable all EDDI related grant deliverables to be achieved
New strategies for DEMO design criteria and interactions with WPMAT and Designers needs to be established
Integration of WPMAT (via EDDI) within the high level frameworks, such as the system engineering approach, to DEMO needs to be established
Improved and long term “working level” strategy for EDDI needs to be aligned within the roadmap

## Slide 21
Logos of the official WPMAT participants. Note: Some universities and labs are grouped in certain countries and, therefore, appear officially as only one RU (CIEMATand 2 sections of ENEA). Nevertheless, you are invited to add your own logo!